May

23

How to make a Gantt chart in Excel 2010 and 2013


by [Svetlana Cheusheva](https://plus.google.com/114460563248390451831?rel=author) [Excel](https://www.ablebits.com/office-addins-blog/tag/excel/), [Excel charts](https://www.ablebits.com/office-addins-blog/tag/excel-charts/), [Excel tips](https://www.ablebits.com/office-addins-blog/tag/excel-howto/) [78 Comments](https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/#comments)

If you were asked to name three key components of Microsoft Excel, what would they be? Most likely, spreadsheets to input data, formulas to perform calculations and charts to create graphical representations of various data types.

I believe, every Excel user knows what a chart is and how to create it. However, one graph type remains opaque to many - the **Gantt chart**. This short tutorial will explain the key features of the Gantt diagram, show how to make a simple Gantt chart in Excel, where to download advanced Gantt chart templates and how to use the online Project Management Gantt Chart creator.

* [What is the Gantt diagram?](https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/#gantt-chart-description)
* [How to make a Gantt chart in Excel](https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/#make-gantt-chart)
* [Excel Gantt chart templates](https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/#gantt-chart-templates)

What is a Gantt chart?

The **Gantt chart** bears a name of Henry Gantt, American mechanical engineer and management consultant who invented this chart as early as in 1910s. A Gantt diagram in Excel represents projects or tasks in the form of cascading horizontal bar charts. A Gantt chart illustrates the breakdown structure of the project by showing the start and finish dates as well as various relationships between project activities, and in this way helps you track the tasks against their scheduled time or predefined milestones.  



How to make Gantt chart in Excel 2010, 2007 and 2013

Regrettably, Microsoft Excel does not have a built-in Gantt chart template as an option. However, you can quickly create a Gantt chart in Excel by using the bar graph functionality and a bit of formatting.

Please follow the below steps closely and you will make a simple Gantt chart in under 3 minutes. We will be using Excel 2010 for this Gantt chart example, but you can simulate Gantt diagrams in Excel 2007 and Excel 2013 exactly in the same way.

1. Create a project table


You start by entering your project's data in an Excel spreadsheet. List each task is a separate row and structure your project plan by including the *Start date*, *End date* and *Duration*, i.e. the number of days required to complete the tasks.


**Tip.** Only the *Start date* and *Duration* columns are really necessary for creating an Excel Gantt chart. However, if you enter the *End Dates* too, you can use a simple formula to calculate *Duration*, as you can see in the screenshot below.  


2. Make a standard Excel Bar chart based on Start date

You begin making your Gantt chart in Excel by setting up a usual *Stacked Bar* chart.

* Select a range of your **Start Dates** with the column header, it's B1:B11 in our case. Be sure to select only the cells with data, and not the entire column.
* Switch to the *Insert* tab > *Charts* group and click **Bar**.
* Under the *2-D Bar* section, click **Stacked Bar**.




As a result, you will have the following Stacked bar added to your worksheet:  



**Note.** Some other Gantt Chart tutorials you can find on the web recommend creating an empty bar chart first and then populating it with data as explained in the next step. But I think the above approach is better because Microsoft Excel will add one data series to the chart automatically, and in this way save you some time.

Step 3. Add Duration data to the chart

Now you need to add one more series to your Excel Gantt chart-to-be.


**1.** Right-click anywhere within the chart area and choose **Select Data** from the context menu.  



The **Select Data Source** window will open. As you can see in the screenshot below, *Start Date* is already added under **Legend Entries (Series)**. And you need to add *Duration* there as well.


**2.** Click the **Add** button to select more data (*Duration*) you want to plot in the Gantt chart.  



**3.** The *Edit Series* window opens and you do the following:


* In the **Series name** field, type "*Duration*" or any other name of your choosing. Alternatively, you can place the mouse cursor into this field and click the column header in your spreadsheet, the clicked header will be added as the *Series name* for the Gantt chart.
* Click the range selection icon C:\Users\ben\Desktop\Gantt Chart_files\range-selection-icon.pngnext to the **Series Values** field.



**4.** A small *Edit Series* window will open. Select your project **Duration** data by clicking on the first Duration cell (D2 in our case) and dragging the mouse down to the last duration (D11). Make sure you have not mistakenly highlighted the header or any empty cell.  


**5.** Click the range selection icon again to exit this small window. This will bring you back to the previous *Edit Series* window with *Series name* and *Series values* filled in, where you click *OK*.  



**6.** Now you are back at the *Select Data Source* window with both *Start Date* and *Duration* added under **Legend Entries (Series).** Simply click *OK* for the Duration data to be added to your Excel chart.  



The resulting bar chart should look similar to this:  


Step 4. Add task descriptions to the Gantt chart


Now you need to replace the days on the left side of the chart with the list of tasks.


**1.** Right-click anywhere within the chart plot area (the area with blue and orange bars) and click **Select Data** to bring up the *Select Data Source* window again.

**2.** Make sure the **Start Date** is selected on the left pane and click the **Edit** button on the right pane, under *Horizontal (Category) Axis Labels*.  


**3.** A small *Axis Label* window opens and you select your tasks in the same fashion as you selected Durations in the previous step - click the range selection icon C:\Users\ben\Desktop\Gantt Chart_files\range-selection-icon.png, then click on the first task in your table and drag the mouse down to the last task. Remember, the column header should not be included. When done, exit the window by clicking on the range selection icon again.  



**4.** Click *OK* twice to close the open windows.

**5.** Remove the chart labels block by right-clicking it and selecting *Delete* from the context menu.  


At this point your Gantt chart should have task descriptions on the left side and look something like this:  



Step 5. Transform the bar graph into the Excel Gantt chart

What you have now is still a stacked bar chart. You have to add the proper formatting to make it look more like a Gantt chart. Our goal is to remove the blue bars so that only the orange parts representing the project's tasks will be visible. In technical terms, we won't really delete the blue bars, but rather make them transparent and therefore invisible.

**1.** Click on any **blue bar** in your Gantt chart to select them all, right-click and choose **Format Data Series** from the context menu.  



**2.** The *Format Data Series* window will show up and you do the following:

* Switch to the *Fill tab* and select **No Fill**.
* Go to the *Border Color* tab and select **No Line**.




**Note.** You do not need to close the dialog because you will use it again in the next step.

**3.** As you have probably noticed, the tasks on your Excel Gantt chart are listed in **reverse order**. And now we are going to fix this.

Click on the list of tasks in the left-hand part of your Gantt chart to select them. This will display the *Format Axis* dialog for you. Select the **Categories in reverse order option** under *Axis Options* and then click the *Close* button to save all the changes.  


The results of the changes you have just made are:

* Your tasks are arranged in a proper order on a Gantt chart.
* Date markers are moved from the bottom to the top of the graph.



Your Excel chart is starting to look like a normal Gantt chart, isn't it? For example, my Gantt diagram looks like this now:  


Step 6. Improve the design of your Excel Gantt chart


Though your Excel Gantt chart is beginning to take shape, you can add a few more finishing touches to make it really stylish.

**1. Remove the empty space on the left side of the Gantt chart.**

As you remember, originally the starting date blue bars resided at the start of your Excel Gantt diagram. Now you can remove that blank white space to bring your tasks a little closer to the left vertical axis.

* Right-click on the **first Start Date** in your data table, select *Format Cells > General*. Write down the number that you see - this is a numeric representation of the date, in my case 41730. As you probably know, Excel stores dates as numbers based on the number of days since 1-Jan-1900. Click *Cancel* because you don't actually want to make any changes here.  
  
* Click on any date above the task bars in your Gantt chart. One click will select all the dates, you right click them and choose **Format Axis** from the context menu.  
  
* Under *Axis Options*, change **Minimum** to **Fixed** and type the number you recorded in the previous **step.**

**2. Adjust the number of dates on your Gantt chart.**


In the same *Format Axis* window that you used in the previous step, change **Major unit** and **Minor unit** to **Fixed** too, and then add the numbers you want for the date intervals. Typically, the shorter your project's timeframe is, the smaller numbers you use. For example, if you want to show every other date, enter 2 in the *Major unit*. You can see my settings in the screenshot below:  



**Tip.** You can play with different settings until you get the result that works best for you. Don't be afraid to do something wrong because you can always revert to the default settings by switching back to Auto in Excel 2010 and 2007, or click *Reset* in Excel 2013.

**3. Remove excess white space between the bars.**

Compacting the task bars will make your Gantt graph look even better.

* Click any of the orange bars to get them all selected, right click and select **Format Data Series**.
* In the Format Data Series dialog, set **Separated** to **100%** and **Gap Width** to **0%** (or close to 0%).




And here is the result of our efforts - a simple but nice-looking Excel Gantt chart:  


Remember, though your Excel chart simulates a Gantt diagram very closely, it still keeps the main features of a standard Excel chart:

* Your Excel Gantt chart will resize when you add or remove tasks.
* You can change a Start date or Duration, the chart will reflect the changes and adjust automatically.
* You can [save your Excel Gantt chart as an image](http://www.ablebits.com/office-addins-blog/2013/08/27/save-excel-chart-as-image/) or [convert to HTML and publish online](http://www.ablebits.com/office-addins-blog/2014/03/21/convert-excel-html/).

**Tips:**

* You can design your Excel Gant chart in different ways by changing the fill color, border color, shadow and even applying the 3-D format. All these options are available in the **Format Data Series** window (right-click the bars in the chart area and select *Format Data Series* from the context menu).  
  
* When you have created an awesome design, it might be a good idea to save your Excel Gantt chart as a template for future use. To do this, click the chart, switch to the *Design* tab on the ribbon and click **Save as Template**.

[Download this Gantt chart example](https://cdn.ablebits.com/_img-blog/gantt-chart/xls/gannt-chart.xlsx).


Excel Gantt chart templates

As you see, it's not a big problem to build a simple Gantt chart in Excel. But what if you want a more sophisticated Gantt diagram with percent-complete shading for each task and a vertical *Milestone* or *Checkpoint* line? Of course, if you are one of those rare and mysterious creatures whom we respectively call "Excel gurus", you can try to make such a graph on your own, with the help of this article: [Advanced Gantt Charts in Microsoft Excel](http://peltiertech.com/Excel/Charts/GanttChart.html).

However, a faster and more stress-free way would be using an Excel Gantt chart template. Below you will find a quick overview of several project management Gantt chart templates for different versions of Microsoft Excel.


Gantt chart template for Excel 2013 from Microsoft

This Excel Gantt chart template, called **Gantt Project Planner**, is purposed to track your project by different activities such as *Plan Start* and *Actual Start*, *Plan Duration* and *Actual Duration* as well as *Percent Complete*.


In Excel 2013, this template is available directly on the *File > New* tab. If you cannot find it there, you can download it from Microsoft's web-site - [Gantt Project Planner template](http://office.microsoft.com/en-us/templates/gantt-project-planner-TC102887601.aspx). This template requires no learning curve at all, simply click on it and it's ready for use.  


Online Gantt chart template

This is an *Interactive Online Gantt Chart Creator* from smartsheet.com. As well as the previous Gantt chart template, this one is fast and easy-to-use. They offer 30 days free trial, so you can sign with your Google account [here](https://www.smartsheet.com/s/online-gantt-chart) and start making your first Excel Gantt diagram online straight away.

The process is very straightforward, you enter your project details in the left-hand table, and as you type a Gantt Chart is being built in the right-hand part of the screen.  


Gantt chart template for Excel, Google Sheets and OpenOffice Calc

[Gantt chart template](http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html) from vertex42.com is a free Gantt chart template that works with Excel 2003, 2007, 2010 and 2013 as well as OpenOffice Calc and Google Sheets. You work with this template in the same fashion as you do with any normal Excel spreadsheet. Simply enter the start date and duration for each task and define % in the *Complete* column. To change the range of dates displayed in the Gantt chart area, slide the scroll bar.  


And finally, one more Gant chart Excel template for your consideration.

Project Manager Gantt Chart template

[Project Manager Gantt Chart](http://www.professionalexcel.com/project-manager-gantt-chart/) from professionalexcel.com is also a free project management Gantt chart template for Excel that can help track your tasks against their allocated time. You can choose either the standard weekly view or daily for short term projects.

Hopefully, at least one of the above-mentioned Gantt chart Excel templates is well suited for your needs. If not, you can find plenty more Gantt chart templates on the web.

Now that you are familiar with the main features of the Gantt diagram, you can explore it further and create your own sophisticated Gantt charts in Excel to amaze your boss and co-workers : )